## Sheet1
Order Number | Change Request Title | Work Classification | Priority | Application Name | IT Directorate | IT Division | IT Section | Manager ID | Effort Cost | Capacity to Deliver | Actuals | Cost Variance | Cost Variance Percentage
161454 | Sub-Project-1 | 1 | 1 | Application A | DIR-1 | Div-1 | Sec-1 | 485317370 | 149149.4219 | 1 | 470545.583 | -321396.1612 | -215.486
161454 | Sub-Project-1 | 1 | 1 | Application B | DIR-2 | Div-2 | Sec-2 | 485317562 | 35203.4805 | 1 | 8830.17 | 26373.3105 | 74.9168
161454 | Sub-Project-1 | 1 | 1 | Application C | DIR-1 | Div-3 | Sec-3 | 486437960 | 30286 | 1 | 69890.0067 | -39604.0067 | -130.7667
161454 | Sub-Project-1 | 1 | 1 | Application D | DIR-3 | Div-4 | Sec-4 | 484909766 | 34726 | 1 | 13018.6333 | 21707.3667 | 62.5104
161454 | Sub-Project-1 | 1 | 1 | Application E | DIR-4 | Div-5 | Sec-5 | 485093174 | 0 | 0 | 0 | 0 | 0
161454 | Sub-Project-1 | 1 | 1 | Application A | DIR-1 | Div-1 | Sec-6 | 485317372 | 30544 | 1 | 14789.1506 | 15754.8494 | 51.5808
161454 | Sub-Project-1 | 1 | 1 | Application F | DIR-1 | Div-6 | Sec-7 | 484878760 | 39062.3799 | 1 | 51832.86 | -12770.4801 | -32.6925
161454 | Sub-Project-1 | 1 | 1 | Application G | DIR-1 | Div-6 | Sec-8 | 484666160 | 94317.5 | 1 | 150693.8376 | -56376.3376 | -59.7729
161454 | Sub-Project-1 | 1 | 1 | Application H | DIR-1 | Div-1 | Sec-9 | 484878160 | 49126 | 1 | 74047.011 | -24921.011 | -50.7288
161454 | Sub-Project-1 | 1 | 1 | Application I | DIR-1 | Div-3 | Sec-10 | 486438760 | 35262 | 1 | 67243.4074 | -31981.4074 | -90.6965
161454 | Sub-Project-1 | 1 | 1 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 29437 | 1 | 30002.1256 | -565.1256 | -1.9198
161097 | Sub-Project-2 | 2 | 2 | Application B | DIR-2 | Div-2 | Sec-2 | 485317562 | 35203.4805 | 1 | 8830.17 | 26373.3105 | 74.9168
161097 | Sub-Project-2 | 2 | 2 | Application D | DIR-3 | Div-4 | Sec-12 | 484909766 | 35762 | 1 | 39055.9 | -3293.9 | -9.2106
161097 | Sub-Project-2 | 2 | 2 | Application H | DIR-2 | Div-7 | Sec-13 | 485288562 | 34179.0996 | 1 | 622918 | -588738.9004 | -1722.5114
161097 | Sub-Project-2 | 2 | 2 | Application J | DIR-2 | Div-8 | Sec-14 | 484061586 | 31742 | 0 | 0 | 31742 | 100
161097 | Sub-Project-2 | 2 | 2 | Application K | DIR-2 | Div-8 | Sec-14 | 484061586 | 34126 | 1 | 0 | 34126 | 100
161097 | Sub-Project-2 | 2 | 2 | Application L | DIR-4 | Div-5 | Sec-15 | 485093172 | 0 | 1 | 0 | 0 | 0
161127 | Sub-Project-3 | 1 | 2 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 55303 | 1 | 56364.6958 | -1061.6958 | -1.9198
161127 | Sub-Project-3 | 1 | 2 | Application B | DIR-2 | Div-2 | Sec-2 | 485317562 | 35203.4805 | 1 | 8830.17 | 26373.3105 | 74.9168
161199 | Sub-Project-4 | 1 | 1 | Application D | DIR-3 | Div-4 | Sec-16 | 484909760 | 36466 | 1 | 22862.6815 | 13603.3185 | 37.3041
161199 | Sub-Project-4 | 1 | 1 | Application A | DIR-1 | Div-1 | Sec-6 | 485317372 | 26029 | 1 | 12603.0252 | 13425.9748 | 51.5808
161199 | Sub-Project-4 | 1 | 1 | Application E | DIR-4 | Div-5 | Sec-5 | 485093174 | 0 | 0 | 0 | 0 | 0
161199 | Sub-Project-4 | 1 | 1 | Application M | DIR-1 | Div-1 | Sec-9 | 484878160 | 29926 | 1 | 45107.089 | -15181.089 | -50.7288
161199 | Sub-Project-4 | 1 | 1 | Application I | DIR-1 | Div-3 | Sec-10 | 486438760 | 40238 | 1 | 76732.4663 | -36494.4663 | -90.6965
161199 | Sub-Project-4 | 1 | 1 | Application A | DIR-1 | Div-1 | Sec-1 | 485317370 | 29414.5 | 1 | 92798.637 | -63384.137 | -215.486
161199 | Sub-Project-4 | 1 | 1 | Application C | DIR-1 | Div-3 | Sec-3 | 486437960 | 30286 | 1 | 69890.0067 | -39604.0067 | -130.7667
161199 | Sub-Project-4 | 1 | 1 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 29437 | 1 | 30002.1256 | -565.1256 | -1.9198
161199 | Sub-Project-4 | 1 | 1 | Application D | DIR-3 | Div-4 | Sec-4 | 484909766 | 34726 | 1 | 13018.6333 | 21707.3667 | 62.5104
161214 | Sub-Project-5 | 1 | 2 | Application B | DIR-2 | Div-2 | Sec-2 | 485317562 | 35203.4805 | 1 | 8830.17 | 26373.3105 | 74.9168
161214 | Sub-Project-5 | 1 | 2 | Application F | DIR-1 | Div-6 | Sec-17 | 484878760 | 33597.1396 | 1 | 51832.86 | -18235.7204 | -54.2776
161214 | Sub-Project-5 | 1 | 2 | Application D | DIR-3 | Div-4 | Sec-16 | 484909760 | 50366.9395 | 1 | 31577.9985 | 18788.9409 | 37.3041
161214 | Sub-Project-5 | 1 | 2 | Application D | DIR-3 | Div-4 | Sec-4 | 484909766 | 34726 | 1 | 13018.6333 | 21707.3667 | 62.5104
161214 | Sub-Project-5 | 1 | 2 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 228605.2031 | 1 | 232993.9196 | -4388.7165 | -1.9198
161214 | Sub-Project-5 | 1 | 2 | Application N | DIR-2 | Div-7 | Sec-18 | 485291760 | 35048.5 | 1 | 98835.64 | -63787.14 | -181.9968
161274 | Sub-Project-6 | 2 | 4 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 29437 | 1 | 30002.1256 | -565.1256 | -1.9198
161274 | Sub-Project-6 | 2 | 4 | Application G | DIR-1 | Div-6 | Sec-8 | 484666160 | 33126 | 1 | 52926.3823 | -19800.3823 | -59.7729
161277 | Sub-Project-7 | 2 | 1 | Application I | DIR-1 | Div-3 | Sec-10 | 486438760 | 40238 | 1 | 76732.4663 | -36494.4663 | -90.6965
161277 | Sub-Project-7 | 2 | 1 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 69960.3984 | 1 | 71303.484 | -1343.0856 | -1.9198
161277 | Sub-Project-7 | 2 | 1 | Application E | DIR-4 | Div-5 | Sec-5 | 485093174 | 0 | 0 | 0 | 0 | 0
161277 | Sub-Project-7 | 2 | 1 | Application L | DIR-4 | Div-5 | Sec-15 | 485093172 | 0 | 1 | 0 | 0 | 0
161277 | Sub-Project-7 | 2 | 1 | Application A | DIR-1 | Div-1 | Sec-6 | 485317372 | 35841.5996 | 1 | 17354.2042 | 18487.3954 | 51.5808
161277 | Sub-Project-7 | 2 | 1 | Application O | DIR-4 | Div-5 | Sec-19 | 485093170 | 0 | 0 | 0 | 0 | 0
161277 | Sub-Project-7 | 2 | 1 | Application C | DIR-1 | Div-3 | Sec-3 | 486437960 | 30286 | 1 | 69890.0067 | -39604.0067 | -130.7667
161376 | Sub-Project-8 | 1 | 1 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 39783.4004 | 1 | 40547.1541 | -763.7537 | -1.9198
161385 | Sub-Project-9 | 1 | 1 | Application E | DIR-4 | Div-5 | Sec-5 | 485093174 | 0 | 0 | 0 | 0 | 0
161385 | Sub-Project-9 | 1 | 1 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 44956.5996 | 1 | 45819.6673 | -863.0677 | -1.9198
161385 | Sub-Project-9 | 1 | 1 | Application L | DIR-4 | Div-5 | Sec-15 | 485093172 | 0 | 0 | 0 | 0 | 0
161388 | Sub-Project-10 | 2 | 2 | Application P | DIR-5 | Div-9 | Sec-20 | 486439960 | 29851 | 1 | 43173.34 | -13322.34 | -44.6295
161388 | Sub-Project-10 | 2 | 2 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 29437 | 1 | 30002.1256 | -565.1256 | -1.9198
161388 | Sub-Project-10 | 2 | 2 | Application P | DIR-5 | Div-9 | Sec-21 | 486440760 | 34566 | 1 | 130353.76 | -95787.76 | -277.1155
158394 | Sub-Project-11 | 1 | 3 | Application Q | DIR-5 | Div-10 | Sec-22 | 485107668 | 30802 | 1 | 394194 | -363392 | -1179.7675
158394 | Sub-Project-11 | 1 | 3 | Application R | DIR-1 | Div-6 | Sec-23 | 484877960 | 29918 | 1 | 121183.12 | -91265.12 | -305.0509
158394 | Sub-Project-11 | 1 | 3 | Application G | DIR-1 | Div-6 | Sec-8 | 484666160 | 67126 | 1 | 107249.1801 | -40123.1801 | -59.7729
158394 | Sub-Project-11 | 1 | 3 | Application S | DIR-5 | Div-11 | Sec-24 | 485593762 | 815982 | 1 | 634237.5467 | 181744.4533 | 22.2731
158394 | Sub-Project-11 | 1 | 3 | Application T | DIR-5 | Div-11 | Sec-24 | 485593762 | 132542 | 1 | 103020.7933 | 29521.2067 | 22.2731
140106 | Sub-Project-12 | 2 | 2 | Application U | DIR-3 | Div-12 | Sec-25 | 485106560 | 53476 | 1 | 50182 | 3294 | 6.1598
140106 | Sub-Project-12 | 2 | 2 | Application V | DIR-2 | Div-8 | Sec-26 | 485286960 | 31741 | 1 | 31072.3 | 668.7 | 2.1067
140106 | Sub-Project-12 | 2 | 2 | Application W | DIR-2 | Div-13 | Sec-27 | 485288568 | 32769.6201 | 1 | 32768.94 | 0.68012 | 0.0020755
140106 | Sub-Project-12 | 2 | 2 | Application B | DIR-2 | Div-2 | Sec-28 | 485317562 | 35326.2998 | 1 | 35320.68 | 5.6198 | 0.015908
140106 | Sub-Project-12 | 2 | 2 | Application X | DIR-6 | Div-14 | Sec-29 | 485486760 | 29526 | 1 | 14560.59 | 14965.41 | 50.6855
140106 | Sub-Project-12 | 2 | 2 | Application X | DIR-6 | Div-14 | Sec-29 | 485486760 | 29526 | 1 | 14560.59 | 14965.41 | 50.6855
140106 | Sub-Project-12 | 2 | 2 | Application Y | DIR-6 | Div-14 | Sec-30 | 485486766 | 34576 | 1 | 35125.84 | -549.84 | -1.5902
159417 | Sub-Project-13 | 1 | 2 | Application Z | DIR-2 | Div-8 | Sec-31 | 485317568 | 36588 | 1 | 25617.06 | 10970.94 | 29.9851
159417 | Sub-Project-13 | 1 | 2 | Application H | DIR-2 | Div-7 | Sec-11 | 485288562 | 54828 | 1 | 55880.5769 | -1052.5769 | -1.9198